## Slide 1: Santé Innovations
Monica Menniti - Health Care Consultant
Vann Nguyen - Design Consultant
Samppa Valkama - Lead Software Developer
Ashley McNeill - Business Consultant
Sampo Savolainen - Developer/ Animator

## Slide 2
Who are we?
An international, multi-professional team of specialists.
What do we do?
We create multi-platform health promotion media.

## Slide 3: Business Idea
Preventative/promotional health care is cost effective!
We create media with a focus on health promotion
Experts from different fields to create motivational, exciting, effective products for promoting health in different areas
Examples of possible clients:
  companies wanting to promote health in the work place
    Increased employee health = more productive employees and less sick days
  Health insurance companies wanting to take preventative health measures to avoid the cost of serious illness among their clients
  Public health awareness such as organ donation, weight-loss, stop smoking campaigns, overall healthy habits

## Slide 4: Red Cross Project
Creating a quick motivator for blood donor candidates
Emphasis on blood donation:
  SAVES LIVES!
  Is quick and easy
Target audience:
  Young adults, first time donators
  Older donators that need a ‘‘reminder“ about the importance of donation

## Slide 5: SWOT Analysis
Internal
STRENGTH
Newest information about media technology
Representatives from different professions
OPPORTUNITIES
Large potential client base and income
Improving public health while generating profit
THREATS
Competition from advertising agencies
Other start-up companies wanting to capitalize on the same industry
External
WEAKNESS
Limited time, resources, and budget

## Slide 6: Core ideas of animation
PAIN
A little pinch can make you a lifesaver
SAFETY
You cannot get HIV or any other diseases from donating
TIME
30 minutes of your time can save 3 lives
Every …. days you can donate blood
AGE
With 18 years you can start donating
STATISTICS
154.000 Finns donate per year
Only 3% of the Finn-population donates (What’s your excuse?)
How often? Regular donations are important! Make it a habit!
Regular donors assure sufficient blood supply

## Slide 7: User stories
As a user I can watch the animation with different devices (phones, tablets and computers)
As a user I can watch the animation at the RC website, facebook site, info screens, or wherever (it's multi-platform)
As a user I can interact with the animation by clicking or tapping (eg. Pause by tapping)
As a user I can mute the background music of the animation

## Slide 8: Action plan for next 2 weeks
Common tasks: preparing for the sales pitch especially the questions, brainstorming about action plan and user testing
Monica: prepare for sales pitch
Samppa: work on demo, create edge animation
Ashley: research market size, prepare user testing
Vann: work on demo, create edge animation
Sampo: work on demo, create edge animation

## Slide 9: Santé Innovations, 6.9.2012
Status:
Describe here the current status
  Business plan, project goals
  Presentation for steering group
Next steps:
Come up with a catchy, professional company name
Begin planning stages of animation
Begin research/information collection for content
Further development of business model (financial, marketing, etc)
Risks:
Animation is not smart and/or fun enough to motivate people
Client does not like product
Contingency plan:
Brainstorming, creativity
Market research on sceen at blood donation center

## Slide 10: Santé Innovations, 13.9.2012
Status:
Describe here the current status
  Business model canvas drafted
  Updated project plan
Next steps:
SWOT analysis
Consult with TTL
Begin planning stages of animation
Begin research/information collection for content
Further development of business model (financial, marketing, etc)
Risks:
Animation is not smart and/or fun enough to motivate people
Client does not like product
Contingency plan:
Brainstorming, creativity
Market research on sceen at blood donation center

## Slide 11: Santé Innovations, 20.9.2012
Status:
Describe here the current status
  Started story board
  Brain storming about animation (watched exsisting videos)
  Got information about blood donation (statistics) acording to current research
  Develop user stories
Next steps:
Continue planning stages and development of animation
Further development of business model (financial, marketing, etc)
Risks:
Animation is not smart and/or fun enough to motivate people
Client does not like product
Contingency plan:
Brainstorming, creativity
Market research on sceen at blood donation center

## Slide 12: Santé Innovations, 27.9.2012
Status:
Describe here the current status
  Made progress on story board
  Made our marketing plan
  Finnished user stories
Next steps:
Continue planning stages and development of animation
Further development of business model (financial, marketing, etc) including research
Risks:
Animation is not smart and/or fun enough to motivate people
Client does not like product
Contingency plan:
Brainstorming, creativity
Market research on sceen at blood donation center

## Slide 13: Santé Innovations, 04.10.2012
Status:
Describe here the current status
  Steeringgroup meeting
  Polished story board contend
  Marketanalysis research contunied
  Brainstorming sales-pitch
Next steps:
Continue planning stages and development of animation
Further development of business model (financial, marketing, etc) including research
Develop sales pitch to customers for mid term evaluation
Risks:
Animation is not smart and/or fun enough to motivate people
Client does not like product
Contingency plan:
Brainstorming, creativity
Market research on sceen at blood donation center

## Slide 14: Santé Innovations, 17.10.2012
Status:
Describe here the current status
  Almost finished sales-pitch
  Finished demo (flash)
Next steps:
Continue planning stages and development of animation
Further development of business model (financial, marketing, etc) including research
Develop sales pitch to customers for mid term evaluation
Risks:
Animation is not smart and/or fun enough to motivate people
Client does not like product
Contingency plan:
Brainstorming, creativity

## Slide 15: Action plan for entire project
Prototype, end of period 1
  Business model canvass completed
  Marketing plan
  Financial plan
  Draft, demo of animation
  Field research phase 1 completed
  User testing
Final product, December
  New client(s)
  Documentation finalized
  Quality, polished final product for client